## Daily Task Report
Daily task report
S: Short-term task (in a day)
L: Long-term task (2+ days)
D: Delayed task
O: On-schedule task
A: Ahead of schedule
# | Task | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10
1 | Review URD | 2020-06-01: L-O; 2020-06-02: S-O
2 | Do SRS | 2020-06-03: L-O; 2020-06-04: L-O; 2020-06-05: L-O; 2020-06-07: S-O
3 | Framework Design | 2020-06-08: L-O; 2020-06-09: L-O; 2020-06-10: L-O
# | Task | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20
1 | Review URD
2 | Do SRS
3 | Framework Design | 2020-06-11: L-O; 2020-06-13: L-O
Note on D12: duytu: + Self assessment URD
Note on E12: duytu: +Team meeting to clarify system requirements.
Note on F13: duytu: + Team meeting to Design Class/Database,Prototype for SRS.
Note on G13: duytu: + Design Prototype for SRS.
Note on H13: duytu: + Write SRS
Note on K14: duytu: Study Spring Boot
Note on L14: duytu + Framework Design
Note on M14: duytu: + Meeting Review SRS + Update CM_plan + Write Meeting 6/10 + Update Framework Design (wait SRS to complete)
Note on D21: duytu: + Coding a Screen Demo with Spring Boot
Note on F21: duytu: + Done Prototype for screen Demo + Fix Bug Docker

## Daily Issue Report
Daily issue report
S: Self-resolve (Plan)
NS: Need to support (Plan)
U: Urgent
NU: Not urgent
D: Very difficult to resolve
# | Task | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10
1 | Review URD | 2020-06-01: S-NU; 2020-06-02: NS-NU
2 | Do SRS | 2020-06-03: S-U; 2020-06-04: S-NU; 2020-06-05: S-NU; 2020-06-07: S-NS
3 | Framework Design | 2020-06-08: S-NU; 2020-06-09: S-NU; 2020-06-10: S-U
# | Task | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20
1 | Review URD
2 | Do SRS
3 | Framework Design | 2020-06-11: S-NU; 2020-06-13: S-NU
Note on E12: duytu + Team have QA about URD need PM answer (Will send by Team Leader).
Note on F13: duytu: + Answer QA, detail in email Daily report 06/03/2020.
Note on H13: duytu:
Note on J13: duytu: Send SRS to PM Review
Note on M14: duytu: + 6/11 Project configuration and Code a screen + Update Database Design.
Note on F21: duytu: + Error Docker could not start sql server. => Will simulate data if unable to fix.