## Defects
MEETING MINUTES
Project | WLS
Topic | Kick off project
Date | 2020-05-31
Time | 20:00 - 21:15
Location | Facetime Facebook
Conductor | HieuTN
Written by | TuND
Attendees | HieuTN, NhiHY, TuND, QuangNN
Send to | All attendees
Actions:
| ID | Action | PIC | Deadline
| 1 | Overview of knowledge of team members | HieuTN
| 2 | Choose Framework, Library | TuND | 2020-06-07
| 3 | In general about the Restful API | NhiHY,HieuTN
| 4 | Choose group name | QuangNN
Conclusions:
| ID | Conclusion
| 1 | All members have fairly average knowledge backend and frontend.
| 2 | Wait for the "Work Logging System" document to choose, currently 40% Spring MVC,60% Spring Boot. Use jQuery for event handling. Maven for software project management.
| 3 | Know the definition, how it works, if the project is used to will further research. Research support tools: Postman.
| 4 | Group name : A2Z
Attachments:
| ID | Attachment
| 1 | #
| 2 | https://docs.spring.io/spring-boot/docs/current/reference/htmlsingle/#appendix
| 3 | https://topdev.vn/blog/restful-api-la-gi/
| 4 | #
Notes:
Note on E15: PC: Person in charge